## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Saally | Blake | Tony | Adrian | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 4 |  | 0
|  | Design architecture | Project Manager | Adrian | 4
| Requirements |  |  |  |  | 6 |  | 2
|  | Gather | Requirements Engineer | Blake | 2 |  | 2
|  | Analyze | Requirements Engineer | Saally | 2
|  | Specify | Requirements Engineer | Saally | 2
| Documentation |  |  |  |  | 26 |  | 13
|  | Project Charter | Project Manager | Blake, Saally, Tony, Adrian | 4 |  | 5 |  | 1 | 1 | 2 | 0 | 4
|  | Release Plan | Project Manager | Blake | 3
|  | Requirements Document | Project Manager, Requirements Engineer | Blake, Saally, Tony, Adrian | 4 |  | 8 |  | 4 | 1 | 1 | 2 | 8
|  | Project Plan | Project Manager, Developers | Blake | 4
|  | Architecture Document | Architect | Adrian | 3
|  | Test Report | Tester | Tony | 4
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Saally | 4
Coding
Iteration 1: | Development |  |  |  |  | 26 |  | 25
|  | Determine technology needs | Developer | Blake, Saally, Tony, Adrian | 6 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Research and learn new language and environment | Developer | Blake, Saally, Tony, Adrian | 8 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Project Charter | Developer | Tony, Adrian | 2 |  | 5 |  | 1 | 1 | 2 | 0 | 4
|  | Project Requirements (Document) | Developer | Tony, Saally | 3 |  | 8 |  | 4 | 1 | 1 | 2 | 8
|  | Begin Front end framework | Developer | Blake, Saally | 6 |  | 4 |  | 0 | 2 | 2 | 0 | 4
|  | Work on Released Plan | Project Manager | Blake | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Analysis |  |  |  |  | 4 |  | 4
|  | Requirement Analysis | Project Manager | Saally | 2 |  | 2 |  | 2 | 0 | 0 | 0 | 2
|  | Plan iteration 2 | Project Manager | Blake | 2 |  | 2 |  | 0 | 2 | 0 | 0 | 2
Iteration 2: | Design |  |  |  |  | 8 | 12
|  | Decide on which languages to use for web development (python? javascript?) | Developer | Blake, Saally, Tony, Adrian | 4 |  | 6
|  | Look at tutorials on https://reactjs.org/ | Developer | Blake, Saally, Tony, Adrian | 4 |  | 6
| Development |  |  |  |  | 14 | 16
|  | Continue work on Log in Page | Developer | Blake, Tony | 4 |  | 4
|  | Start prototype for Managing a Deck of cards (create a set) | Developer | Saally, Adrian | 4 |  | 6
|  | Prototype for Managing a Deck of cards (add/delete a card) | Developer | Saally, Blake | 3 |  | 3
|  | Prototype for Managing a Deck of cards (edit a card) | Developer | Tony, Adrian | 3 |  | 3
| Analysis |  |  |  |  | 6 | 6
|  | Prepare Technical Prototype Presentation | Project Manager | Blake, Saally, Tony, Adrian | 4 |  | 4
|  | Plan Iteraition 3 | Project Manager | Saally | 2 |  | 2
Iteration 3: | Design
Development
Analysis
Iteration 4: | Design
Development
Analysis
Iteration 5: | Design
Development
Analysis
Total |  |  |  |  | 94 | 94 | 112 | 44